## sudarshan
DATE	Module Assigned	Task- (function)	Sub task- feature developed	complexity	dependent module	functional validation	output screen generated	status	fixing the bug	reviewed by	tested by
20/08/2014 to 26/08/2014	setting moodule -mange subjects	generate normal subjects	select batch		batch module		select batch screen	done
			add normal subject				add normal subject modal dailog box	done
			edit normal subject				edit normal subject modal dailog box	done
			delete normal subject				add elective group modal dialog box	done
			ajax functionality	medium			add elective subject modal dailog box	done
		generate elective group and subject	select batch for elective group				edit elective subject modal dailog box	done
			create a elevtive groups				assign subject to student	done
			edit delete elective group					done
			add elective subject to particular elective group					done
			edit delete elective subject					done
			assign elective subject to particular batch student					done
			ajax functionality	complex

	student module	search	search by first name and last name		course module		student serch detail screen	done
			view search		batch module		view all screen	done
			select on searched name		guardian module		view student for selected batch	done
			view profile		student previous data module		student profile screen	done
			edit profile		student previous subject mark		Gaurdian edit screen	done
			report, delete, send email, guardians		category module		student report	done
			pdf report for student		country module		edit student details screen	done
			ajax functionality	complex			send mail screen	done
		view all	select batch				pdf report screen	done
			view student for particular student					done
			select student					done
			view profile					done
			ajax functionality	medium				done

8/27/2014	User- module	create user	create user				create user
			encrypt password with salt and join with salt				display user
			user validation				change password
			change password	complex

8/28/2014			search user				search user
			view all user				view all user
			view profile				profile view
			edit user				edit user
			delete user
			ajax functionality	medium

8/30/2014

## sachin
DATE	Module Assigned	Task- (function)	Sub task- feature developed	complexity	dependent module	functional validation	output screen generated	status	fixing the bug	reviewed by	tested by
20/08/2014 to 23/08/2014	News	CRUD operation on News module	generate a news		user module		news display	Complete		Prateema
			delete a news	Average			news create
			display a news

			Edit news				Update news	Complete
			Delete news				Delete news from database

		Association	Association between news and comments	Average			Add the multiple comment to the single news	Complete
8/25/2014	News	validation and GUI	validation of text and other functionality	Simple			validates all screens	Complete

8/26/2014	Attendance	Select batch and association with student	Uderstanfd the whole module and perform one task i.e select batch	average			Display only one screen select batch	Incomplete
8/26/2014	Attendance & News Module Defect	Select batch	fetch the student from the batch	simple			Display second screen	Incomplete
	& News Defect	Defect report	Solve 90 % defect					Incomplete
lacking to deliver the module

## kanikshk
20/08/2014 to 27/08/2014	Module Assigned	Task- (function)	Sub task- feature developed	complexity	dependent module	functional validation	output screen generated	status	fixing the bug	reviewed by	tested by
	news	crud operation on news module	generate a news	average	user module		news display	completed		prateema
			display a news				news create
			delete a news

			edit news	average			update news	completed
			delete news				delete news

	validation of setting module
	manage course	validation	to display course name and section name in same columns
			when we click on save and update button we should get message"course updated /saved succesfully"
			error message should be display properly from top to bottom
			25 more validation

	calender	to create a calender	to display a calender				calender should be display	only example		prateema
		to add a task in it

	calender	to create a calender in proper format					not exact output	not completed
		to add a task ,should display add link					zero productivity
	calender 28/8/2014	to create a calender in proper format					fullcalender	completed		prateema
							also given a link add to it
	calender	to crate a page for add link					crateevent page created	completed		prateema
		to create a show page for the event					show page is created	completed

	proper updation of sheet is required* refere other sheets

## amar
DATE	Module Assigned	Task- (function)	Sub task- feature developed	complexity	dependent module	functional validation	output screen generated	status	fixing the bug	reviewed by	tested by	Task Remaining
20/08/2014 to 26/08/2014	setting module- grading system	generate new grade	create grade
			display grade	medium	Batch and subject	yes	3
			edit grade

	Student-Student Admission	create Guardian details	cerate guardian details.	high	student	no	3

			save guardian details.		Student Previous_details

			maintain association between student and guardian		Student previous_subject_mark

			edit guardian details.

			Select one guardian as emergency contact

		create previous details of student	create student previous details		student	no	1

			maintain record of student previous details

			Maintain Association with student

		create previous_Subject_marks	create previous Subject and marks	High	Student	no	1

			maintain all records of previous subject and marks

			use ajax for displaying previous subject form

			Maintain Association with Student

			validation of all pages	high	all modules	no	8
	proper updation of sheet required

8/27/2014	Student module	Student admission	Auto increament Student admission number genrate and set and done all field validationvalidation	medium

		guardian details	validation of all guardian fields	medium

		immediate contact	save one guardian as immediate contact(later dependancy developed after sms module done)	medium

		previous details	save and validate previous institution details	medium

		previous subject	validates all field of previous subject(only problem in ajax calling to custom method)but done by simple way	high

7/28/2014	Timetabel	Genrate Weekdays	Genrating week days and save it	high	Batch	no	2

			maintainaing assocaiation wit batch

7/30/2014	Calender	Genrate Calender	genrating calender	high	event		2

			add event on perticular date on calender

	Event	Genrating event	Genrat and save event for perticular date	high	calender		3

9/1/2014	Time Tabel	Weekday allocation	Select Batch	complex	Batch		2
			Assign Weekday for that batch(Ajax)
			Maintain Association between Timetabel And Weekday
			Maintain Record of weekdays for batch
							2
	View Timetabel	Displaying Tabel	Select Batch	complex	Batch
			Display Timetabel For that perticular Batch		Weekday
			Display time allocated for perticular peroid
			Display selected Weekday for that Bath

02/09/14	Exam	Exam report	select course and automatic select batches under that course and add that batches in queue for report	omplex	Batch	no	4
					Course

## anuja
DATE	Module Assigned	Task- (function)	Sub task- feature developed	complexity	dependent module	functional validation	output screen generated	status	fixing the bug	reviewed by	tested by
20/08/2014 to 26/08/2014	setting: Student category	generate Student Category	1.create category	medium		done	Category		done	prateema	rohit and tanvi
			2.save category
			3.edit category
			4.delete category

	setting: Batch Transfer	Batch Transfer	1.select course	complex	Course	done	Batch transfer
			2.display course		batch
			3.select Batch		student
			4.edit batch
			5.delete batch
			6.create gardian
			7.Ajax functionlity

	Student :admmission	generate admission form	1.create student parsonal datails	complex	Course	done	Student personal details
			2.select Course and batch for particular student		Batch
			3.select blood group		Category
			4.select category
			5.select country
			6.save all fields in databse

	Setting	bug solving	1. solve defect of all setting module			done

	Time-Table :Class-timings	class-timings	1.finind dependent module		batch
			2.see flow of all time table module from fedena		time table entry
			3.create index page of time table module

	update the dates properly *

8/27/2014	Student deatils: admission	admission	1. validation of admission module	medium	setting	done
					category

			2. insatll ruby and rails
			3. install mysql
			4. install sublime

8/28/2014	Timetabel	Class timing	Crating class timing And maintain record	high	Batch	no	2

			perform all crud operation

			Maintain Association with Batch

8/30/2014			1. Install ruby and rails
			2. insatll sql
			3. insatll sublime

	TimeTable	ClassTiming	1.genearete class timing	complex	Batch	done	class timing
			2. Done all CRUD operation
			3. use ajax for popup
			4. validation of module

9/1/2014	Time Table	Time table create/edit	1.select batch(ajax)	complex	Batch	done	Time Table create/edit
			2.fetch class timing from databse		Class Timnings
			3.fetch weekdays from database		weekdays
			4.select subjects(ajax)		subjects
			5.display timetable

## prateema
DATE	Module Assigned	Task- (function)	Sub task- feature developed	complexity	dependent module	functional validation	output screen generated	status	fixing the bug	reviewed by	tested by
20/08/2014 to 24/08/2014	setting-manage course	generate course	create a course	medium		done	course	done
		generate batch	display course			done
			delete course			done
			edit course			done
			create batch for course			done
			delete particular batch for a course			done
			edit a particular batch for a course			done
			display course and batch			done

	student details	advanced Search	search according to full name	low		done
			search according to admission no.	low		done	advanced search screen
			search according to course	medium	course module		delete student screen	done
			search according to batch	medium	batch module
			search according to date	low
			search according to category	low		done
		display	display the detailed data for student			done

		send mail
		report
		profile	display profile for particular student
8/26/2014	timetable	select batch
		assign weedys to batch
		assign weekdays to all batches common
8/27/2014	system login	login page				partial	login screen
		create timetable	select batch
			disply the batches			done	batch screen
8/28/2014	root page	root page				done	system home screen

## tanvi
Module

## rohit
Date	Module Name	Assigned To	Function	Tested on Date	Defect ID	Review1	Retesting on Date	Unresolved Defect ID	Review2	Defects Reported To	comment	status
8/26/2014	Manage News	Sachin Pawar	Search News	8/26/2014	Def_News_01, Def_News_02, Def_News_03, Def_News_04		8/28/2014	Def_News_01, Def_News_04, Def_News_22.
			Publish News	8/27/2014	Def_News_05, Def_News_07		8/28/2014	Def_News_05
			"Add" News	8/28/2014	Def_News_06, Def_News_10, Def_News_16		8/28/2014	Def_News_16, Def_News_18
			"Update" News	8/29/2014	Def_News_08, Def_News_13, Def_News_17		8/28/2014	Def_News_23.
			View functional flow	8/30/2014	Def_News_09		8/28/2014	Def_News_24
			"Delete" News	8/31/2014	Def_News_11, Def_News_14		8/28/2014
			Leave Comment	9/1/2014	Def_News_12, Def_News_15		8/28/2014	Def_News_19, Def_News_20
			"Edit" News		Def_News_14		8/28/2014
			delete comment	28.08.2014				Def_News_21

8/27/2014	install ruby and rails
	jira defect tracking tool

8/28/2014	Retesting of 'Manage News' module
	CIS Employee Registration and MR Reg. form designed
8/29/2014	holiday
8/30/2014	Retesting defect report for "Manage News' prepared and documented. Ubuntu, Ruby, Rails and MySQL installation

## Defect Report
Defect_Id	Project Name	Module Name	Summary	Description	Suggestions	Severity	Priority	Type of defect	Status Valid/Invalid	Reported to	Reported By	Resolved
Def_News_01	Educulture	Manage News	No error message when user search with blank search field	1.when user searches"news" by keeping field blank it does not show Error message		low	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	No
Def_News_02	Educulture	Manage News	when user finding the particlur news,the label should 'search news " instead of" search"	When user searches specific news, there is search label instead of" Search News"		low	low	Functional	Valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_03	Educulture	Manage News	when user finding the particlur news,the label should 'search " instead of" GO"	when user finding the particlur news,the label should 'search news " instead of" search"	1.when user search for news the label should be" news search" ,instead of that it should be "GO" button.	low	low	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_04	Educulture	Manage News	No error message when user should keep all fields blank or fill field with the invalid data.	when user searches news with invalid string ,it does not show the "Error message" Eg."No matches found with <> news."		medium	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	No
Def_News_05	Educulture	Manage News	1.author name does not display.	1.when user clicks on "publish news"button ,it creates the news but it does not display the Authors name.		medium	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	No
Def_News_06	Educulture	Manage News	1.News "title" &" content" fields are in limited character length	1."News title" accept only 20 characters . It should be long upto (100) characters.		medium	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_07	Educulture	Manage News	1.when user click on publish news button ,during loading process button name not changes to "Please Wait"	1.when user create the news & click on the "publish news button", it does not show the loading process"please wait"	when news published by user, it should display news created time and date	low	low	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_08	Educulture	Manage News	1."update button not working correctly"	1. On view all button update news button to edit the previous news it does not get updated.	when user update news, it shows message which has spelling mistake. it should be "News updated successfully."	medium	medium	Functional	Invalid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_09	Educulture	Manage News	Functional flow is unavailable on each window.	As the user moves on different windows using different functionalities an appropriate flow not displayed on each window	There should an appropriate path on each window. successfully	low	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_10	Educulture	Manage News	no news created message	when user create new news and publish the news, it does not display message. Eg." News published successfully"		medium	medium	Functional	Invalid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_11	Educulture	Manage News	no confirmation message when user click delete link to delete the news	When user click on 'Delete' link to delete the Comment, it does not display Confirmation box. Eg. "Are you sure ? "	delete confirmation box should contain message "Are you sure to delete?"	low	low	Functional	Invalid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_12	Educulture	Manage News	No error message when user leave comment without any content i.e. blank comment	when user left blank the comment text, and click on submit button to leave the comment, it does not display error message Eg."comment can't be blank."		low	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	No
Def_News_13	Educulture	Manage News	Update news not working properly	When user select "View All" and slect specific news to update, somaetimes user able to update changes and sometimes unable		high	high	Functional	Invalid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_14	Educulture	Manage News	Edit News/ Delete News links are not at right top corner	Edit news and delete news links are not at appropriate position,	links should be at right top corner of the window	low	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_15	Educulture	Manage News	For to leave a "comment" button is used.	when user leave comment, there is "Comment" button, that should be "Submit".	Button name should be "Submit"	low	medium	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes
Def_News_16	Educulture	Manage News	News content Editor box is incomplete	when user create a news, News content editor box does not having advanced feature to leave an appropriate content for the news.	Editor box should be with all features	medium	high	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	No
Def_News_17	Educulture	Manage News	user while update the news content, and keep News title and content blank, It does not display any error message	user while update the news content, and keep News title and content blank, It does not display any aerror messages. Eg. "News title cant be blank" and "News content cant be blank."		high	high	Functional	valid	Devesh Sir /Pratima	Rohidas / tanvi	Yes

Def_News_18	Educulture	Manage News	recently created news are displayed at the last position in the list of all news	when user creates news, recently created news are located in the last position in the list of all news, when user view all news	recently created news should display at top positions in the news list
Def_News_19	Educulture	Manage News	comments are displayed above the editor box of comments	when user leave comments,comments are displayed above the editor box	comments should dispaly below the editor box
Def_News_20	Educulture	Manage News	recently added comments are displayed below the previously created comments	when different users "leave the comment" old comment display at the top & recently added comments display at the end of list.	recently added comment should display on the top of list
Def_News_21	Educulture	Manage News	delete news confirmation box has grammatical error in its message	when user delete the news it show conformation delete box with grammatical errors	Delete message should display"Are you sure to delete< news name> ?"
Def_News_22	Educulture	Manage News	search news funtionality requires exact string matching with previously created "news title"	when user search specific news by entering specific strings its unable to search news until & unless exact matching with news title.	when user enters specific string to search news it should display the corresponding news matching with entered string.
Def_News_23	Educulture	Manage News	updated news confirmation box has grammatical error in its message.	when user updated specific news it shows message box with spelling mistake.	when user update the specific news it should display the message "<news added successfully>"
Def_News_24	Educulture	Manage News	Incorrect flow of "back" button.	when user click on "View All"link-->click on specific news -->display news details,on the same window ,when user click on "back" button it moves to "Add" news window instead of "View All "news window.