## sudarshan
DATE | Module Assigned | Task- (function) | Sub task- feature developed | complexity | dependent module | functional validation | output screen generated | status | fixing the bug | reviewed by | tested by
20/08/2014 to 26/08/2014 | setting moodule -mange subjects | generate normal subjects | select batch |  | batch module |  | select batch screen | done
|  |  | add normal subject |  |  |  | add normal subject modal dailog box | done
|  |  | edit normal subject |  |  |  | edit normal subject modal dailog box | done
|  |  | delete normal subject |  |  |  | add elective group modal dialog box | done
|  |  | ajax functionality | medium |  |  | add elective subject modal dailog box | done
|  | generate elective group and subject | select batch for elective group |  |  |  | edit elective subject modal dailog box | done
|  |  | create a elevtive groups |  |  |  | assign subject to student | done
|  |  | edit delete elective group |  |  |  |  | done
|  |  | add elective subject to particular elective group |  |  |  |  | done
|  |  | edit delete elective subject |  |  |  |  | done
|  |  | assign elective subject to particular batch student |  |  |  |  | done
|  |  | ajax functionality | complex
| student module | search | search by first name and last name |  | course module |  | student serch detail screen | done
|  |  | view search |  | batch module |  | view all screen | done
|  |  | select on searched name |  | guardian module |  | view student for selected batch | done
|  |  | view profile |  | student previous data module |  | student profile screen | done
|  |  | edit profile |  | student previous subject mark |  | Gaurdian edit screen | done
|  |  | report, delete, send email, guardians |  | category module |  | student report | done
|  |  | pdf report for student |  | country module |  | edit student details screen | done
|  |  | ajax functionality | complex |  |  | send mail screen | done
|  | view all | select batch |  |  |  | pdf report screen | done
|  |  | view student for particular student |  |  |  |  | done
|  |  | select student |  |  |  |  | done
|  |  | view profile |  |  |  |  | done
|  |  | ajax functionality | medium |  |  |  | done
2014-08-27 | User- module | create user | create user |  |  |  | create user
|  |  | encrypt password with salt and join with salt |  |  |  | display user
|  |  | user validation |  |  |  | change password
|  |  | change password | complex
2014-08-28 |  |  | search user |  |  |  | search user
|  |  | view all user |  |  |  | view all user
|  |  | view profile |  |  |  | profile view
|  |  | edit user |  |  |  | edit user
delete user
|  |  | ajax functionality | medium
2014-08-30 | User- module |  | salt updation
password hashing
creating users
2014-09-01
2014-09-02
2014-09-03 | exam- module | module | reports generation |  |  |  |  | done
|  |  | change linking |  |  |  |  | done
|  |  | generate report center |  |  |  |  | done
|  |  | exam wise report |  |  |  |  | partial

## sachin
DATE | Module Assigned | Task- (function) | Sub task- feature developed | complexity | dependent module | functional validation | output screen generated | status | fixing the bug | reviewed by | tested by
20/08/2014 to 23/08/2014 | News | CRUD operation on News module | generate a news |  | user module |  | news display | Complete |  | Prateema
|  |  | delete a news | Average |  |  | news create
display a news
|  |  | Edit news |  |  |  | Update news | Complete
|  |  | Delete news |  |  |  | Delete news from database
|  | Association | Association between news and comments | Average |  |  | Add the multiple comment to the single news | Complete
2014-08-25 | News | validation and GUI | validation of text and other functionality | Simple |  |  | validates all screens | Complete
2014-08-26 | Attendance | Select batch and association with student | Uderstanfd the whole module and perform one task i.e select batch | average |  |  | Display only one screen select batch | Incomplete
2014-08-26 | Attendance & News Module Defect | Select batch | fetch the student from the batch | simple |  |  | Display second screen | Incomplete
| & News Defect | Defect report | Solve 90 % defect |  |  |  |  | Incomplete
lacking to deliver the module

## kanikshk
20/08/2014 to 27/08/2014 | Module Assigned | Task- (function) | Sub task- feature developed | complexity | dependent module | functional validation | output screen generated | status | fixing the bug | reviewed by | tested by
| news | crud operation on news module | generate a news | average | user module |  | news display | completed |  | prateema
|  |  | display a news |  |  |  | news create
delete a news
|  |  | edit news | average |  |  | update news | completed
|  |  | delete news |  |  |  | delete news
validation of setting module
| manage course | validation | to display course name and section name in same columns
when we click on save and update button we should get message"course updated /saved succesfully"
error message should be display properly from top to bottom
25 more validation
| calender | to create a calender | to display a calender |  |  |  | calender should be display | only example |  | prateema
to add a task in it
| calender | to create a calender in proper format |  |  |  |  | not exact output | not completed
|  | to add a task ,should display add link |  |  |  |  | zero productivity
| calender 28/8/2014 | to create a calender in proper format |  |  |  |  | fullcalender | completed |  | prateema
also given a link add to it
| calender | to crate a page for add link |  |  |  |  | crateevent page created | completed |  | prateema
|  | to create a show page for the event |  |  |  |  | show page is created | completed
proper updation of sheet is required* refere other sheets

## amar
DATE | Module Assigned | Task- (function) | Sub task- feature developed | complexity | dependent module | functional validation | output screen generated | status | fixing the bug | reviewed by | tested by | Task Remaining
20/08/2014 to 26/08/2014 | setting module- grading system | generate new grade | create grade
|  |  | display grade | medium | Batch and subject | yes | 3
edit grade
| Student-Student Admission | create Guardian details | cerate guardian details. | high | student | no | 3
|  |  | save guardian details. |  | Student Previous_details
|  |  | maintain association between student and guardian |  | Student previous_subject_mark
edit guardian details.
Select one guardian as emergency contact
|  | create previous details of student | create student previous details |  | student | no | 1
maintain record of student previous details
Maintain Association with student
|  | create previous_Subject_marks | create previous Subject and marks | High | Student | no | 1
maintain all records of previous subject and marks
use ajax for displaying previous subject form
Maintain Association with Student
|  |  | validation of all pages | high | all modules | no | 8
proper updation of sheet required
2014-08-27 | Student module | Student admission | Auto increament Student admission number genrate and set and done all field validationvalidation | medium
|  | guardian details | validation of all guardian fields | medium
|  | immediate contact | save one guardian as immediate contact(later dependancy developed after sms module done) | medium
|  | previous details | save and validate previous institution details | medium
|  | previous subject | validates all field of previous subject(only problem in ajax calling to custom method)but done by simple way | high
2014-07-28 | Timetabel | Genrate Weekdays | Genrating week days and save it | high | Batch | no | 2
maintainaing assocaiation wit batch
2014-07-30 | Calender | Genrate Calender | genrating calender | high | event |  | 2
add event on perticular date on calender
| Event | Genrating event | Genrat and save event for perticular date | high | calender |  | 3
2014-09-01 | Time Tabel | Weekday allocation | Select Batch | complex | Batch |  | 2
Assign Weekday for that batch(Ajax)
Maintain Association between Timetabel And Weekday
Maintain Record of weekdays for batch
2
| View Timetabel | Displaying Tabel | Select Batch | complex | Batch
|  |  | Display Timetabel For that perticular Batch |  | Weekday
Display time allocated for perticular peroid
Display selected Weekday for that Bath

## anuja
DATE | Module Assigned | Task- (function) | Sub task- feature developed | complexity | dependent module | functional validation | output screen generated | status | fixing the bug | reviewed by | tested by
20/08/2014 to 26/08/2014 | setting: Student category | generate Student Category | 1.create category | medium |  | done | Category |  | done | prateema | rohit and tanvi
2.save category
3.edit category
4.delete category
| setting: Batch Transfer | Batch Transfer | 1.select course | complex | Course | done | Batch transfer
|  |  | 2.display course |  | batch
|  |  | 3.select Batch |  | student
4.edit batch
5.delete batch
6.create gardian
7.Ajax functionlity
| Student :admmission | generate admission form | 1.create student parsonal datails | complex | Course | done | Student personal details
|  |  | 2.select Course and batch for particular student |  | Batch
|  |  | 3.select blood group |  | Category
4.select category
5.select country
6.save all fields in databse
| Setting | bug solving | 1. solve defect of all setting module |  |  | done
| Time-Table :Class-timings | class-timings | 1.finind dependent module |  | batch
|  |  | 2.see flow of all time table module from fedena |  | time table entry
3.create index page of time table module
update the dates properly *
2014-08-27 | Student deatils: admission | admission | 1. validation of admission module | medium | setting | done
category
2. insatll ruby and rails
3. install mysql
4. install sublime
2014-08-28 | Timetabel | Class timing | Crating class timing And maintain record | high | Batch | no | 2
perform all crud operation
Maintain Association with Batch
2014-08-30 |  |  | 1. Install ruby and rails
2. insatll sql
3. insatll sublime
| TimeTable | ClassTiming | 1.genearete class timing | complex | Batch | done | class timing
2. Done all CRUD operation
3. use ajax for popup
4. validation of module
2014-09-01 | Time Table | Time table create/edit | 1.select batch(ajax) | complex | Batch | done | Time Table create/edit
|  |  | 2.fetch class timing from databse |  | Class Timnings
|  |  | 3.fetch weekdays from database |  | weekdays
|  |  | 4.select subjects(ajax) |  | subjects
5.display timetable

## prateema
DATE | Module Assigned | Task- (function) | Sub task- feature developed | complexity | dependent module | functional validation | output screen generated | status | fixing the bug | reviewed by | tested by
20/08/2014 to 24/08/2014 | setting-manage course | generate course | create a course | medium |  | done | course | done
|  | generate batch | display course |  |  | done
|  |  | delete course |  |  | done
|  |  | edit course |  |  | done
|  |  | create batch for course |  |  | done
|  |  | delete particular batch for a course |  |  | done
|  |  | edit a particular batch for a course |  |  | done
|  |  | display course and batch |  |  | done
| student details | advanced Search | search according to full name | low |  | done
|  |  | search according to admission no. | low |  | done | advanced search screen
|  |  | search according to course | medium | course module |  | delete student screen | done
|  |  | search according to batch | medium | batch module
|  |  | search according to date | low
|  |  | search according to category | low |  | done
|  | display | display the detailed data for student |  |  | done
send mail
report
|  | profile | display profile for particular student
2014-08-26 | timetable | select batch
assign weedys to batch
assign weekdays to all batches common
2014-08-27 | system login | login page |  |  |  | partial | login screen
|  | create timetable | select batch
|  |  | disply the batches |  |  | done | batch screen
2014-08-28 | root page | root page |  |  |  | done | system home screen
2014-08-30
2014-09-01
2014-09-02 | Exam-module | created grading level |  |  |  | done
2014-09-03 | Exam-module | create exam |  |  |  | done
|  | created databases for exam |  |  |  | done
|  | git updation |  |  |  | done
|  | integration with previous data |  |  |  | done

## tanvi
Module

## rohit
Date | Module Name | Assigned To | Function | Tested on Date | Defect ID | Review1 | Retesting on Date | Unresolved Defect ID | Review2 | Defects Reported To | comment | status
2014-08-26 | Manage News | Sachin Pawar | Search News | 2014-08-26 | Def_News_01, Def_News_02, Def_News_03, Def_News_04 |  | 2014-08-28 | Def_News_01, Def_News_04, Def_News_22.
|  |  | Publish News | 2014-08-27 | Def_News_05, Def_News_07 |  | 2014-08-28 | Def_News_05
|  |  | "Add" News | 2014-08-28 | Def_News_06, Def_News_10, Def_News_16 |  | 2014-08-28 | Def_News_16, Def_News_18
|  |  | "Update" News | 2014-08-29 | Def_News_08, Def_News_13, Def_News_17 |  | 2014-08-28 | Def_News_23.
|  |  | View functional flow | 2014-08-30 | Def_News_09 |  | 2014-08-28 | Def_News_24
|  |  | "Delete" News | 2014-08-31 | Def_News_11, Def_News_14 |  | 2014-08-28
|  |  | Leave Comment | 2014-09-01 | Def_News_12, Def_News_15 |  | 2014-08-28 | Def_News_19, Def_News_20
|  |  | "Edit" News |  | Def_News_14 |  | 2014-08-28
|  |  | delete comment | 28.08.2014 |  |  |  | Def_News_21
2014-08-27 | install ruby and rails
jira defect tracking tool
2014-08-28 | Retesting of 'Manage News' module
CIS Employee Registration and MR Reg. form designed
2014-08-29 | holiday
2014-08-30 | Retesting defect report for "Manage News' prepared and documented. Ubuntu, Ruby, Rails and MySQL installation

## Defect Report
Defect_Id | Project Name | Module Name | Summary | Description | Suggestions | Severity | Priority | Type of defect | Status Valid/Invalid | Reported to | Reported By | Resolved
Def_News_01 | Educulture | Manage News | No error message when user search with blank search field | 1.when user searches"news" by keeping field blank it does not show Error message |  | low | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | No
Def_News_02 | Educulture | Manage News | when user finding the particlur news,the label should 'search news " instead of" search" | When user searches specific news, there is search label instead of" Search News" |  | low | low | Functional | Valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_03 | Educulture | Manage News | when user finding the particlur news,the label should 'search " instead of" GO" | when user finding the particlur news,the label should 'search news " instead of" search" | 1.when user search for news the label should be" news search" ,instead of that it should be "GO" button. | low | low | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_04 | Educulture | Manage News | No error message when user should keep all fields blank or fill field with the invalid data. | when user searches news with invalid string ,it does not show the "Error message" Eg."No matches found with <> news." |  | medium | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | No
Def_News_05 | Educulture | Manage News | 1.author name does not display. | 1.when user clicks on "publish news"button ,it creates the news but it does not display the Authors name. |  | medium | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | No
Def_News_06 | Educulture | Manage News | 1.News "title" &" content" fields are in limited character length | 1."News title" accept only 20 characters . It should be long upto (100) characters. |  | medium | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_07 | Educulture | Manage News | 1.when user click on publish news button ,during loading process button name not changes to "Please Wait" | 1.when user create the news & click on the "publish news button", it does not show the loading process"please wait" | when news published by user, it should display news created time and date | low | low | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_08 | Educulture | Manage News | 1."update button not working correctly" | 1. On view all button update news button to edit the previous news it does not get updated. | when user update news, it shows message which has spelling mistake. it should be "News updated successfully." | medium | medium | Functional | Invalid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_09 | Educulture | Manage News | Functional flow is unavailable on each window. | As the user moves on different windows using different functionalities an appropriate flow not displayed on each window | There should an appropriate path on each window. successfully | low | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_10 | Educulture | Manage News | no news created message | when user create new news and publish the news, it does not display message. Eg." News published successfully" |  | medium | medium | Functional | Invalid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_11 | Educulture | Manage News | no confirmation message when user click delete link to delete the news | When user click on 'Delete' link to delete the Comment, it does not display Confirmation box. Eg. "Are you sure ? " | delete confirmation box should contain message "Are you sure to delete?" | low | low | Functional | Invalid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_12 | Educulture | Manage News | No error message when user leave comment without any content i.e. blank comment | when user left blank the comment text, and click on submit button to leave the comment, it does not display error message Eg."comment can't be blank." |  | low | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | No
Def_News_13 | Educulture | Manage News | Update news not working properly | When user select "View All" and slect specific news to update, somaetimes user able to update changes and sometimes unable |  | high | high | Functional | Invalid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_14 | Educulture | Manage News | Edit News/ Delete News links are not at right top corner | Edit news and delete news links are not at appropriate position, | links should be at right top corner of the window | low | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_15 | Educulture | Manage News | For to leave a "comment" button is used. | when user leave comment, there is "Comment" button, that should be "Submit". | Button name should be "Submit" | low | medium | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_16 | Educulture | Manage News | News content Editor box is incomplete | when user create a news, News content editor box does not having advanced feature to leave an appropriate content for the news. | Editor box should be with all features | medium | high | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | No
Def_News_17 | Educulture | Manage News | user while update the news content, and keep News title and content blank, It does not display any error message | user while update the news content, and keep News title and content blank, It does not display any aerror messages. Eg. "News title cant be blank" and "News content cant be blank." |  | high | high | Functional | valid | Devesh Sir /Pratima | Rohidas / tanvi | Yes
Def_News_18 | Educulture | Manage News | recently created news are displayed at the last position in the list of all news | when user creates news, recently created news are located in the last position in the list of all news, when user view all news | recently created news should display at top positions in the news list
Def_News_19 | Educulture | Manage News | comments are displayed above the editor box of comments | when user leave comments,comments are displayed above the editor box | comments should dispaly below the editor box
Def_News_20 | Educulture | Manage News | recently added comments are displayed below the previously created comments | when different users "leave the comment" old comment display at the top & recently added comments display at the end of list. | recently added comment should display on the top of list
Def_News_21 | Educulture | Manage News | delete news confirmation box has grammatical error in its message | when user delete the news it show conformation delete box with grammatical errors | Delete message should display"Are you sure to delete< news name> ?"
Def_News_22 | Educulture | Manage News | search news funtionality requires exact string matching with previously created "news title" | when user search specific news by entering specific strings its unable to search news until & unless exact matching with news title. | when user enters specific string to search news it should display the corresponding news matching with entered string.
Def_News_23 | Educulture | Manage News | updated news confirmation box has grammatical error in its message. | when user updated specific news it shows message box with spelling mistake. | when user update the specific news it should display the message "<news added successfully>"
Def_News_24 | Educulture | Manage News | Incorrect flow of "back" button. | when user click on "View All"link-->click on specific news -->display news details,on the same window ,when user click on "back" button it moves to "Add" news window instead of "View All "news window.